## GO-1
Annual Procurement Plan (2022-2023)
( Improvement of Socio-Economic and Livelihood Development of Tribal People Through Integrated Livestock Project)
Budget : Development
Ministry/Division: |  |  |  | : Ministry of Fisheries & Livestock
Agency |  |  |  | : Department of Livestock Services
Procuring Entity Name |  |  |  | : Upazilla Livestock Officer.
Project/Programme Name & Code |  |  |  | : Upazilla Livestock Office & Veterinary hospital, Bochaganj, Dinajpur. | [9 empty] | Code : 224294000
Package No. | Description of Procurement Package (Goods) | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Funds | Estimated Cost (Tk. In lakh) | Advertise Tender | Not used in goods | Advertisement | Tender opening | Tender evaluation | Approval to award | Notification of award | Signing of contract | Total time to contract signing | Time for Completion of Contract
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
GD-1, Lot-1 | CI Sheet : Measurement- 30''X8' Thickness-20 mm | No. | 502 | RFQ | ULO | GOB |  | Planned Dates |  | 2022-12-05 | 2022-12-12 | 2022-12-19 | 12/22/2022 Tentative | 2022-12-26 | 0 | 20Days | 15 Days
| Mesurement-RCC Piller (Round Post) 3 ‘’ Diameter X 9’ Length 6.5 mm rod and GI Wire tie . | No. | 1004 |  |  |  |  | Days |  | 0 | 7 | 7 | 3 | 3
| Total of GD- 1, Lot-1 |  | 1506 |  |  |  |  | Actual Dates
GD-2, Lot-1 | Name: Heavy Floor Mate, Dimension(mm): 1017x507x29, Weight(KG):2.54(±2%), Material: Poly Propylene(PP)/HDPE , Colour-Red/Blue, Load (Ton):3.5, Others: Both Side Lock System, Racking Facility, High Load Capacity ,Environment Friendly ,Long Life, Chemical Resistance and Cold Storage As Per Consumer Demand and Branding Of DTLP Produced from Virgin Poly Propylene. | Nos | 1255 | RFQ | ULO | GOB |  | Planned Dates |  | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-22 | 2022-12-26 | 0 | 20Days | 15 Days
[8 empty] | Days |  | 0 | 7 | 7 | 3 | 3
| Total of GD- 2, Lot -1 |  | 1255 |  |  |  |  | Actual Dates
Grand Total |  |  | 2761
(Wv. †gvQv: †mvqvBev AvLZvi)
Dc‡Rjv cÖvwYm¤ú` Awdmvi
‡evPvMÄ, w`bvRcyi¦