## download (7)
IMPORTANT RURAL INFRASTRUCTURES DEVELOPMENT PROJECT-3 (IRIDP-3)
Monthly Progress Report (Physical & Financial )
District : Dinajpur
Reporting Date : 20,September, 2022
Upazila | Package No | Name_Of_Scheme_With_Location | Tender ID | Quantity |  | Salvage Cost | Name Of Contract | Date Of Contract | Contract Amount (Tk.) |  |  | Planed Completion Date | Physical Progress | Financial Progress | Payment |  | Phasing Of Work | Remark | P.G Validity Date
|  |  |  | Road (km) | Stracture (m) |  |  |  | Road | Stracture | Total |  |  |  | Payment Made | Remaining Payment
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Upazila | PackageNo | Name_Of_Scheme_With_Location | Road Id | Quantity |  | Salvage Cost | Name Of Contract | Date Of Contract | Contract Amount (Tk.) |  |  | Planed Completion Date | Physical Progress | Financial Progress |  |  | PhasingOfWork | Remark
|  |  |  | Road (Km) | Stracture (m) |  |  |  | Road | Stracture | Total |  |  |  | Payment Made | Remaining Payment
2 | 3 | 4 | 5 | 6 | 7 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 25 | 26 | 28 | 29 | 30 | 31
Birol | IRIDP-3/DNJ/DW-11 | [A](1) Improvement of Ramchandropur to Nihal gram Kugber Dokan road at Ch.00m-1216m. [R.ID.(A)127175116][A] (2)Construction of 03 nos 0.625mx0.600m Culvert at Ch.412m,671m&812m, on the same road[B] Improvement of Kashidanga GC to Mongolpur GC via Mill Danga Bazer road at Ch. 3000m-3810m.[R.ID.(B)127172007] | 539092 | 2.026 | 1.88 | 0 | Md. Abul Kalam Azad | 2021-04-20 | 16739020.4 | 247510.63 | 16986531.03 | 2022-04-27 | 100% | 19% | 3300000 | 13686531.03 | Work Completed |  | 2022-09-29
Birol | IRIDP-3/DNJ/DW-12 | [A](1) Improvement of Mirabon Nona Bridge to Bishwnath GP School Ghat road at Ch.1250m-2250m.[R.ID.(A)127174015][A](2) Construction of 01 nos 2.00mx1.50m Culvert at Ch.975m,on the same road[A](3) Construction of 03 nos 0.625mx0.600m Culvert at Ch.1280m,1568m & 1818m, on the same road(B) Improvement of Dhamoir UP Office-Kashidanga GC road at Ch.00-1000m. [R.ID.(B)127173021] | 539093 | 2 | 3.88 | 0 | Md. Abul Kalam Azad | 2021-04-20 | 13970035.91 | 893865.19 | 14863901.1 | 2022-04-27 | 100% | 0% | 0 | 14863901.1 | Work Completed |  | 2022-09-29
Birol | IRIDP-3/DNJ/DW-52 | (1) Improvement of Balandorhat to Bairagi para road at Ch. 00m-1000m..[R.ID.127174006](2) Construction of 02 nos 0.6250mx0.600m Culvert at Ch.488m,534m, on the same road(3) Construction of 01 nos 1.500mx1.500m Culvert at Ch.789m, on the same road | 643544 | 1 | 2.75 | 0 | M/S. Rafi Traders | 2022-03-03 | 7461980.55 | 785786.49 | 8247767.04 | 2023-03-09 | 0% | 0% | 0 | 8247767.04 |  | 28 Days Letter Issued | 31-Dec-23
Birol | IRIDP-3/DNJ/DW-53 | (1) Improvement of Mongolpur old UP Office to Fulbari hat via Shishgram road at Ch. 3920m-5670m.[R.ID.127174079](2) Construction of 01 nos 2x3.000mx3.000m Culvert at Ch.5662m, on the same road(3) Construction of 05 nos 0.6250mx0.600m Culvert at Ch.4103m,4683m,4789m,5126m,5277m, on the same road | 643545 | 1.75 | 9.13 | 0 | M/S. A.K Traders | 2022-03-03 | 13306501.33 | 2278455.22 | 15584956.55 | 2023-03-09 | 10% | 0% | 0 | 15584956.55 | Structure Work on going |  | 2023-05-23
Birol | IRIDP-3/DNJ/DW-54 | (1) Improvement of Mongolpur old UP Office- Mahetabpur Bazar road at Ch. 2140m-2870m. .[R.ID.127174081] (2) Construction of 01 nos 0.6250mx0.600m Culvert at Ch.2145m, on the same road(3) Construction of 01 nos 1.500mx1.500m Culvert at Ch.2321m, on the same road | 643546 | 0.73 | 2.13 | 0 | M/S. Rupali Enterprise | 2022-02-24 | 5773809.07 | 673273.85 | 6447082.92 | 2022-06-30 | 70% | 14% | 935000 | 5512082.92 | WBM Completed, |  | 2023-02-22
Birol | IRIDP-3/DNJ/DW-55 | (1) Improvement of Dinajpur Bochaganj RHD to Kanchon Notunpara road at Ch.00-345m. [R.ID.127175108] (2)Construction of 01 nos 2x3.00mx3.000m Rcc Box Culvert at Ch.286m, on the same road | 643547 | 0.34 | 6 |  | M/S. Quality Construction | 2022-03-10 | 2521468.12 | 1830860.65 | 4352328.77 | 2022-09-22 | 0% | 0% | 0 | 4352328.77 |  | 28 Days Letter Issued | 2023-03-01
Birol | IRIDP-3/DNJ/DW-96 | (a) Improvement of Noyamala GP School RHD to Mokleshpur School Road .(Ch.00 -750m) [R.ID.127174010](b)Construction of 02 nos 0.625mx0.600m. Culvert at Ch.4m,250mon the same road. | 717719 | 0.75 | 1.25 | 0 | MS. Hasibul Traders |  | 5201272.8 | 205705.4 | 5406978.2 |  | 0% | 0% | 0 | 5406978.2
|  | sub total: |  | 8.596 | 27.02 | 0 |  |  | 64974088.18 | 6915457.43 | 71889545.61 | Average= | 40% | 4.714% | 4235000 | 67654545.61